## Sheet1
Software/System | Current State Description | Desired State Description | Gap Description | Impact | Priority | Recommended Actions
Inventory Management System | The current system is manual, relies on spreadsheets, and lacks real-time updates. Inventory data is often inaccurate, leading to overstocking and stockouts. | The desired state is to implement an automated inventory management system with real-time tracking and alerts. We want to ensure accurate, up-to-date inventory data to optimize stock levels and minimize losses. | Gap: Lack of automation, real-time tracking, and inventory accuracy. | High | High | 1. Research and select an appropriate inventory management software with real-time tracking and alerts. 2. Plan data migration from spreadsheets to the new system. 3. Integrate the new system with existing processes and systems. 4. Train staff on using the new system for accurate data entry and real-time monitoring.
Customer Relationship Management (CRM) | We are using a basic CRM that lacks features for lead tracking, customer segmentation, and automated email marketing. Sales and marketing teams struggle to manage leads and tailor marketing campaigns. | We want to upgrade to an advanced CRM with lead tracking, segmentation, and automated email marketing capabilities. This will help us efficiently manage leads, segment customers for personalized marketing, and automate email campaigns. | Gap: Limited CRM functionality for lead management and customer segmentation. | Moderate | Medium | 1. Evaluate and select a comprehensive CRM solution with lead tracking, segmentation, and email automation. 2. Develop a data migration plan to transfer existing CRM data to the new system. 3. Provide training to the sales and marketing teams on using the advanced CRM features effectively.
Website Content Management | Our current content management system (CMS) is outdated and not user-friendly for non-technical staff. Content editors struggle to update the website, resulting in delays in publishing new content. | We aim to transition to a modern, user-friendly CMS for easier content updates and publishing by non-technical staff. This will improve the speed and efficiency of content updates on our website. | Gap: Outdated and non-user-friendly CMS causing delays in content updates. | Low | Low | 1. Research and choose a user-friendly CMS that meets the needs of non-technical content editors. 2. Plan the migration of existing content to the new CMS. 3. Provide training to content editors to ensure they can efficiently use the new system for content updates.